## Start here
InnovaForge Toolkit
Start here
Templates and worksheets for the five stages, from spark to scale
Prof. Dr. Mohamed Fawzi Elgendi
www.fawzooz.ai
How to use it
• Fill in the white cells. Cream cells are calculated for you.
• Open with the canvas and Ignite together at kick-off; revisit the canvas at every milestone.
• Close each stage on the Gates sheet before moving on. If a criterion is not met, loop back.
• The printable edition (PDF) has every sheet, including those drawn by hand: the mind map, the storyboard, the sketch.
The five stages
Stage | Exit criteria
1 · Ignite | One to three prioritized problems or opportunities and a bank of initial ideas, recorded on the canvas.
2 · Forge | A clear value proposition and a low-fidelity prototype ready for first feedback.
3 · Temper | Core assumptions validated or invalidated with real user data; learnings and pivots recorded.
4 · Sculpt | A roadmap with objectives and success metrics agreed by the team and stakeholders.
5 · Polish | Initial performance data analyzed and a decision taken: iterate, scale or sunset. The cycle begins anew.
Licence: CC BY-SA 4.0. You may copy, adapt and share these templates, including commercially, with credit and under the same licence.

## 0.2 Canvas
InnovaForge Toolkit · 0.2
Canvas
The single source of truth: one row per stage, three boxes each.
Project
1 · Ignite | Problems & opportunities | Inspiration sources | Idea bank
The Spark of Insight
2 · Forge | Concept statement | Value proposition | Low-fi prototype
Shaping the Concept
3 · Temper | Riskiest assumptions | User feedback | Learnings & pivots
Testing and Iteration
4 · Sculpt | Goals & OKRs | Roadmap & sprints | Resources & risks
Planning for Impact
5 · Polish | Launch plan | Impact metrics | Next step
Launch, Learn, and Scale

## 1.1 Five Whys
InnovaForge Toolkit · 1.1
Five Whys
Start from a fact you have seen; ask “why?” of each answer.
The problem we observed
Why? | Because…
Why? 1
Why? 2
Why? 3
Why? 4
Why? 5
Root cause, in one sentence

## 1.2 Inspiration
InnovaForge Toolkit · 1.2
Inspiration
Reports, competitors, customers and unrelated fields: what you saw and what it suggests.
Source | What we saw | What it suggests
Reports and research
Competitors
Customers
Customers
An unrelated field
An unrelated field
The pattern across sources

## 1.3 Idea bank
InnovaForge Toolkit · 1.3
Idea bank
Defer judgment, build on others’ ideas, go for quantity. Vote only at the end.
How might we…?
# | Idea | From (brainstorm, provocation…) | Votes
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40

## 1.4 Prioritize
InnovaForge Toolkit · 1.4
Prioritize
Score 1 (low) to 5 (high). The total and the rank are calculated; keep the top one to three.
Problem or opportunity | Impact | Urgency | Evidence | Fit | Total | Rank

## 2.1 Concept
InnovaForge Toolkit · 2.1
Concept
Purpose, audience and features; then the value in one sentence, and a thirty-minute Lean Canvas.
Purpose: what it is for
Audience: who it is for
Features: what it does
Concept statement: For … who …, … is a … that … . Unlike …, it … .
Value proposition, in one sentence
Lean Canvas (after Maurya, 2012)
Box | Our answer
1 Customer segments
2 Problem
3 Unique value proposition
4 Solution
5 Channels
6 Revenue streams
7 Cost structure
8 Key metrics
9 Unfair advantage

## 2.2 SCAMPER
InnovaForge Toolkit · 2.2
SCAMPER
At least one answer per prompt; star the two or three that change the value most.
The idea we are working on
Prompt | Our answers | ★
S · Substitute
C · Combine
A · Adapt
M · Modify
P · Put to another use
E · Eliminate
R · Reverse

## 3.1 Assumptions
InnovaForge Toolkit · 3.1
Assumptions
Importance and evidence from 1 to 5. Important assumptions with weak evidence come first.
# | We believe that… | Type | Importance 1–5 | Evidence 1–5 | Risk score | Quadrant
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15

## 3.2 Tests
InnovaForge Toolkit · 3.2
Tests
One row per test. Write “We are right if…” before the test runs.
# | Assumption # | We believe that… | Method | Users | We measure | We are right if… | What happened | Verdict
1
2
3
4
5
6
7
8
9
10
11
12

## 3.3 Feedback log
InnovaForge Toolkit · 3.3
Feedback log
Five to ten users per cycle. What they did comes before what they said.
Cycle | User | What they did | What they said | Surprise | Assumption ±

## 3.5 Build–Measure–Learn
InnovaForge Toolkit · 3.5
Build–Measure–Learn
Every cycle ends in a decision on evidence: persevere, or pivot.
Cycle | What we built | What we measured | What we learned | Decision
1
2
3
4
5
6
7
8
Pivot record
From | To | The evidence that made us turn

## 4.1 SWOT
InnovaForge Toolkit · 4.1
SWOT
Tie the solution to the mission first; then pair the quadrants into roadmap items and risks.
The line of our mission or strategy it serves, and how
Strengths (inside) | Weaknesses (inside)
Opportunities (outside) | Threats (outside)
Strength × opportunity → roadmap item | Weakness × threat → risk

## 4.3 OKRs
InnovaForge Toolkit · 4.3
OKRs
Each key result needs a baseline and a target. Enter the current value to see progress; Polish tracks these.
Objective | Key result | Baseline | Target | Current | Progress | Owner | By

## 4.4 Roadmap
InnovaForge Toolkit · 4.4
Roadmap
Three to six months by workstream; then the first sprints as user stories.
Workstream | Month 1 | Month 2 | Month 3 | Month 4 | Month 5 | Month 6
Product
People and skills
Users and market
Operations
Milestones
Sprints and user stories
Sprint | As a…, I want…, so that… |  |  | Done when |  | Status

## 4.5 Resources and risks
InnovaForge Toolkit · 4.5
Resources and risks
Likelihood and impact from 1 to 3; the score is calculated. Six and above: act now.
Resource: people, tools, space | How much | Cost
Total budget
Risk | Likelihood 1–3 | Impact 1–3 | Score | Response | Owner

## 5.1 Launch checklist
InnovaForge Toolkit · 5.1
Launch checklist
Nothing ships until every line is Yes or consciously waived.
Kind of launch: full, or phased (who gets it, from when, and go on if…)
Item | Done | Owner
The key results from Sculpt have a baseline.
Tracking is live, and someone owns the dashboard.
Users have a channel for feedback, and someone reads it.
Support knows what is coming and how to answer.
There is a way back if something breaks.
Someone is on call for the first days.
Legal, privacy and security have signed off.
Stakeholders and users have been told.
The retrospective is booked, two to four weeks out.
The canvas is up to date.
Ready

## 5.2 Impact tracker
InnovaForge Toolkit · 5.2
Impact tracker
Track the key results and KPIs from Sculpt from day one. Read the trend, not a single number.
Key result or KPI | Baseline | Target | Week 1 | Week 2 | Week 4 | Progress | Trend
What the numbers say

## 5.3 Retrospective
InnovaForge Toolkit · 5.3
Retrospective
Two to four weeks after launch, with the whole team.
What worked | What did not | What we learned
Actions
Action | Owner | By when

## 5.4 Decision
InnovaForge Toolkit · 5.4
Decision
Decide on the data, then hand the next Ignite what this cycle found.
The decision
Choose: iterate, scale or sunset
The evidence behind the decision
What scaling, iterating or closing will need
Seeds for the next Ignite: problems this cycle uncovered
Ideas we parked
What we will do differently

## ✓ Gates
InnovaForge Toolkit · ✓
Gates
Close each stage only when every criterion is Yes.
Stage 1 · Ignite
Criterion | Met? | Evidence
We looked beneath the surface issue and wrote down a root cause, not a symptom.
Inspiration came from at least three kinds of source, one of them an unrelated field.
We brainstormed with judgment switched off, and kept every idea in the bank.
One to three problems or opportunities are ranked by priority.
The three Ignite boxes on the canvas are filled in.
Gate
Stage 2 · Forge
Criterion | Met? | Evidence
The concept statement names its purpose, its audience and its features.
The value proposition fits in one sentence that someone outside the team understands.
The Lean Canvas is complete, and its riskiest boxes are marked.
A low-fidelity prototype exists: a sketch, a wireframe or a future press release.
The three Forge boxes on the canvas are filled in.
Gate
Stage 3 · Temper
Criterion | Met? | Evidence
The riskiest assumptions were named before anything was built.
Each test had a success signal written down before it ran.
Five to ten real users took part in each cycle.
Every core assumption is marked validated or invalidated, with its evidence.
Learnings and pivots are recorded, and the three Temper boxes on the canvas are filled in.
Gate
Stage 4 · Sculpt
Criterion | Met? | Evidence
The solution is tied to a line of the mission or strategy, in writing.
Each objective has measurable key results, with a baseline and a target.
The roadmap covers three to six months, broken into sprints and user stories.
Resources, budget and the top risks are on paper, each risk with an owner.
The team and the stakeholders have agreed the roadmap and its success metrics.
Gate
Stage 5 · Polish
Criterion | Met? | Evidence
The launch followed its checklist, full or phased as planned.
The OKRs and KPIs set in Sculpt were tracked from day one.
A retrospective was held two to four weeks after launch.
A decision was taken on the data: iterate, scale or sunset.
The lessons are written into the next Ignite, and the cycle begins anew.
Gate